6COSC023C Final Year Project - 2025/26 Timeline

| Week | Date or Deadline | Events / Project Deliverables / Milestones | Who is responsible? |
| --- | --- | --- | --- |
| Semester 1 |  |  |  |
| S1_W1 | 26 Sep 25 | Attend lecture 1 - Introduction to the module and PPRS Go through the course Blackboard site, read the module handbook, timeline, supervisors, and possible topics | Students |
| S1_W2 | 03 Oct 25 | Attend Lecture 2 – Literature Review Request for Project Supervision form deadline. | Student submits form (via BB) |
| S1_W3 | 10 Oct 25 | Attend Lecture 3 – Project Management Assignment of supervisors completed and communicated to students. | Students Module Leader |
| S1_W4 | 17 Oct 25 | Attend Lecture 4 – Project requirements gathering and documentation Attend individual supervision meetings 1 | Students Supervisors set the date of the meeting within these two weeks |
| S1_W5 | 24 Oct 25 | Attend Lecture 5 – Ethical and Legal considerations – Ethics forms Attend individual supervision meetings 1 |  |
| S1 – W6 | 31 Oct 25 | Engagement week - Self-study - PPRS | Students |
| S1_W7 | 7 Nov 25 | Attend Lecture 6 – Project life cycle, software, toolkit, prototyping, Using Gen AI | Students |
| S1_W8 | 13 Nov 25 14 Nov 25 | Summative Assessment 1: PPRS Deadline (Ethics Forms must be included [compulsory]) Attend Lecture 7 – Application Design – User Interface, data visualisation | Student submits (via BB) Students |
| S1_W9 S1_W10 | 21 Nov 25 28 Nov 25 | Student Presentations Mark & feedback on PPRS | Students The Supervisor sets the date of the meeting and provides an online link |
| S1_W11 | 5 Dec 25 | Attend Lecture 8 – Introduction to IPD | Students |
| S1_W12 | - | Milestone: Refined Project Requirements Attend an individual supervision meeting | Students |
| Semester 2 |  |  |  |
| S2_W1 S2_W2 | 23 Jan 26 30 Jan 26 | Milestone: prototype, Initial implementation code Attend an individual supervision meeting | Student present during the meeting. |
| S2_W3 | 05 Feb 26 | Summative assessment 2: IPD Deadline | Student submits PPRS + Ethical forms (via BB) |
| S2_W5 S2_W6 | 13 Feb 26 20 Feb 26 | Student Presentations Mark & feedback on IPD | Students The Supervisor sets the date of the meeting and provides an online link |
| S2_W7 | 27 Feb 26 | Mark & feedback on IPD | Supervisor gives IDP feedback |
| S2_W8 | 6 Mar 26 | Attend Lecture 9 – Implementation and Testing | Students |
| S2_W9 | 13 Mar 26 | Attend Progress Review Meetings | The student calls the meeting |
| S2_W10 | 13 Mar 26 | Attend Lecture 10 – Academic Report writing Attend Progress Review Meetings | Student The student calls the meeting |
| S2_W11 | 20 Mar 26 | Self-Study - Lecture 11 – Final Project submissions & Viva requirements – recorded session | Student |
| S2_W12 | 27 Mar 26 | Attend an individual supervision meeting and get final feedback | The student calls the meeting |
| April | 23 Apr 26 | - Summative assessment 3 – Part 1: Final Project Report & Final Project Code (FPR & FPC) Deadline - Viva arrangements | Student submits (via BB) |
| May | 30 Apr 26 19 May 26 | Summative assessment 3 – part 2: Final Project Viva (FPV) Student Presentations | The supervisor calls a meeting and provides an online link Student presents (assessed orally) |
| Summer Period (Referred/Deferred only) |  |  |  |
| June | - |  |  |
| July | 2 July 26 | Summative assessment - Refer/Defer - [REF/DEF] Summative assessment 1: PPRS - [REF/DEF] Summative assessment 2: IPD - [REF/DEF] Summative assessment 3 – part 1: FYP (FPR & FPC) | Student submits (via BB) |
| July | 27 Feb 26 | Summative assessment Student Presentations / Viva | The Supervisor sets the date of the meeting and provides an online link |

| BLUE cells | indicate milestones to be initiated by the student |
| --- | --- |
| ORANGE cells | indicate milestones to be initiated by the supervisor |
| NB: other regular project meetings can be (pre)arranged between individual supervisors & students at their own convenience. In the table, you can find suggested weeks. |  |